## Sheet1
1st sprint :feature 2:- | [6 empty] | 1st sprint : feature 1
| 6h | 2018-03-09 | Zenab Ahmed | analysis for requerment | Analysis | sign up | 6h | 2018-03-04 | Momen | analysis for requerment | Analysis | log in (Home page)
| 6h | 2018-03-09 | Yosef | analysis for what this feature must to do |  |  | 6h | 2018-03-04 | Eman Reda | analysis for what this feature must to do
| 6h | 2018-03-09 | Ereny Karm | Design for login page | Design |  | 12h | 2018-03-04 | Alaa Rafat | Design for login page | Design
| 6h | 2018-03-09 | Momen | Design for database of login |  |  | 12h | 2018-03-04 | Zenab Ahmed | Design for database of login
| 12h | 2018-03-10 | Alaa Rafat | imblimente for login page | implimintation |  | 24h | 2018-03-05 | Alaa Rafat | imblimente for login page | Implimentation
| 12h | 2018-03-10 | Alaa Rafat | imblimente for database of login |  |  | 24h | 2018-03-06 | Ereny Karm | imblimente for database of login
| 6h | 2018-03-11 | Eman Reda | test design of login it work | Test |  | 12h | 2018-03-07 | Yosef | test design of login it work | Test
| 6h | 2018-03-11 | Ereny Karm | test database it work |  |  | 12h | 2018-03-07 | Eman Reda | test database it work
| 6h | 2018-03-11 | Zenab Ahmed | modify on design of log in page | Modification |  | 12h | 2018-03-08 | Alaa Rafat | modify on design of log in page | Modification
| 6h | 2018-03-11 | Alaa Rafat | modify on database |  |  | 12h | 2018-03-08 | Ereny Karm | modify on database
| 2nd sprint :feature 2:- | [5 empty] | 2nd sprint : feature 1:-
[5 empty] | Analysis | pay online |  |  |  |  | Analysis | Payment Methods
[5 empty] | Design | [5 empty] | Design
[5 empty] | Implimentation | [5 empty] | Implimentation
[5 empty] | Test | [5 empty] | Test
[5 empty] | Modification | [5 empty] | Modification
| 3rd sprint :feature 2:- | [5 empty] | 3rd sprint : feature 1:-
[5 empty] | Analysis | service |  |  |  |  | Analysis | commpanies offers
[5 empty] | Design | [5 empty] | Design
[5 empty] | Implimentation | [5 empty] | Implimentation
[5 empty] | Test | [5 empty] | Test
[5 empty] | Modification | [5 empty] | Modification
| 4th sprint :feature 2:- | [5 empty] | 4th sprint : feature 1:-
[5 empty] | Analysis | customer evaluation |  |  |  |  | Analysis | map clarify
[5 empty] | Design | [5 empty] | Design
[5 empty] | Implimentation | [5 empty] | Implimentation
[5 empty] | Test | [5 empty] | Test
[5 empty] | Modification | [5 empty] | Modification